## Sheet1
Modul/Application | PIC (Person In Charge) | Users | Status | Detail Work | Weight | Actual Progress (%) | Duration (Week) | Due date | Remarks
A. HR SYSTEM ( JOB CODE 7-4001-00-0000 )
Personal Data (HR System) | Deden/Indra |  |  | 1. Sub module development (general info, family, education, employee record, employment history, etc) | 40% | 100% |  |  | done
|  |  |  | 2. Develop tools for upload all information related to Employee Personal Data | 30% | 100% |  |  | done
|  | HRD | On Going | 3. Reporting | 30% | 100% |  |  | done
|  |  |  | a. Additional filtering |  |  |  |  | done
|  |  |  | b. Export report to Excel & PDF |  |  |  |  | done
Personal Data Summary |  |  |  |  | 100% | 100% |  |  | Update Personal Data (BPJS Report)
Resignation/ Pensioun/Contract Status | Deden/Indra |  |  | 1. Resignation form entry & approval | 30% | 100% |  |  | done
|  |  |  | a. link to penalty calculation menu when choose approviate resign type |  |  |  |  | done
|  |  |  | b. new action required, Cancel Request --> before & after approval |  |  |  |  | done
|  | HRD | On Going | c. Email sent to HR team when new resign request submitted |  |  |  |  | done
|  |  |  | d. Email sent to employee & HR team when resign request approved |  |  |  |  | done
|  |  |  | 2. Monitoring / Tracking form | 10% | 100% |  |  | done
|  |  |  | 3. Penalty Calculation | 30% | 100% |  |  | done
|  |  |  | 4. Termination Award | 30% | 100% |  |  | done
Appraisal (New Module ) | Deden |  |  | 1. Database design and perform DDL | 5% | 100%
|  |  |  | 2. Key Result Area input | 25% | 100%
a. Job Accountability Related Performance
b. Basic Supporting Skills and Pro' value
c. Final Rating Page
d. Improvement and Recommendation
|  |  |  | 3. Create KRA approval flow | 5% | 100%
|  |  |  | 4. Appraisal input based on KRA items (Department view) | 10% | 100%
|  | HRD | On Going | 5. Approval appraisal (Division view) | 5% | 100%
|  |  |  | 6. Revisioning appraisal input | 5% | 100%
|  |  |  | 7. Monitoring employee appraisal status and Dept. completion percentage (HRD view) | 10% | 100%
|  |  |  | 8. Create Appraisal Summary | 25% | 100%
a. Get related information (WL, Attendance, dll)
b. Display Curve result
|  |  |  | 9. Reporting | 5% | 100%
|  |  |  | 10. Module for BOD Review and Adjustment | 5% | 100% |  |  | Additional feature
Appraisal |  |  |  |  | 100% | 100% |  |  | This week issue : - Additional feature to upload Management Degree as Annual Appraisal result, will be related to Personal Data system
Appraisal for Contract Staff | Deden | HRD | On Going | 1. Database design and perform DDL | 5% | 100%
|  |  |  | 2. Create Module to Insert Main Data (CS staff who will end on following 3/4 months | 10% | 100%
|  |  |  | 3. Create Module to Insert Attendance Data | 10% | 100%
|  |  |  | 4. Create Mandatory Form B Input | 5% | 100%
|  |  |  | 5. Create User's Appraisal performance entry | 10% | 100%
|  |  |  | 6. Create 1st and 2nd Rater Comment and Recommendation | 5% | 100%
|  |  |  | 7. Create Promotion Section | 5% | 100%
|  |  |  | 8. Create Additional Form B Section | 5% | 100%
|  |  |  | 9. Create Form B menu for User / Supervisor in HO | 10% | 100%
|  |  |  | 10. Create Comment History Section | 5% | 100%
|  |  |  | 11. Create Appraisal CS Tracking menu | 5% | 100%
|  |  |  | 12. Create Appraisal CS Approval menu | 5% | 100%
|  |  |  | 13. Create Appraisal CS Progress Tracking | 5% | 100%
|  |  |  | 14. Create Appraisal CS Setting Menu | 5% | 100%
|  |  |  | 15. Create Appraisal CS Summary | 10% | 100%
Appraisal for Contract Staff |  |  |  |  | 100% | 100% |  |  | This week issue : - cont to develop additional feature to upload Management Degree regarding employee status, whether will be continue as CS, or become RS or it will be completion.
Resignation Summary |  |  |  |  | 100% | 100%
Pre Assignment (Check List) | Deden/Indra |  |  | 1. Create new Pre-Assignment | 40% | 100% |  |  | done
|  |  |  | a. Email notification regarding documents preparation for assignee |  |  |  |  | done
|  |  |  | b. Send email to PAD |  |  |  |  | done
|  | HRD | On Going | 2. Monitoring Pre-Assignment status, both for HRD & employee concern | 40% | 100% |  |  | done
|  |  |  | a. Updating UI based on user feedback |  |  |  |  | done
|  |  |  | b. Email notification regarding documents preparation for assignee |  |  |  |  | done
|  |  |  | 3. Orientation Documents, based on location | 20% | 100% |  |  | done
Pre Assignment Summary |  |  |  |  | 100% | 100%
(MICA Extention) CL/EF/EL Report | Indra |  |  | 1. Generate data for monitoring & reporting purpose | 30% | 100% |  |  | done
|  | HRD | On Going | 2. Monitoring purpose --> action to be execute : counseling, send email, warning letter | 40% | 100% |  |  | done
|  |  |  | 3. Reporting --> weekly & monthly | 30% | 100% |  |  | done
Training System Phase 1 (Without Training Plan Master Input) | Deden | HRD | On Going | 1. Database design and perform DDL | 10% | 100%
|  |  |  | 2. Create Module Training Main Input | 10% | 0%
|  |  |  | 3. Create Module Training Participant Input | 10% | 0%
|  |  |  | 4. Create Module Training Action History Input | 5% | 0%
|  |  |  | 5. Create Module Training Tracking By Requestor and Initiator | 10% | 0%
|  |  |  | 6. Create Module Training Department Approval | 5% | 0%
|  |  |  | 7. Create Module Training Division Approval | 5% | 0%
|  |  |  | 8. Create Module Training HRD Review | 5% | 0%
|  |  |  | 9. Built Print Out Training Request | 5% | 0%
|  |  |  | 10. Built Method Calculate Bonding Period | 5% | 0%
|  |  |  | 11. Built function to Upload Training attendance, report and training material | 10% | 0%
|  |  |  | 12.Create Module Training Reporting | 20% | 0%
Training System |  |  |  |  | 100% | 10%
HR System Progress |  |  |  |  | 85%
B. PCCIS & RFAP (JOB CODE 7-4004-00-0001)
Project Cost Control(PCCIS) | Indra & Jeremy | PAD/COST | Start | 1. Gathering requirements & Study existing system / procedure | 5% | 100% |  |  | done
|  |  |  | 2. Create Flow chart, Identify modification on SOFI, Create database structure | 5% | 100% |  |  | done
|  |  |  | 3. Project Cost Setup (Contract Value, MH Rate, MH Planning, Breakdown budget per FWBS), with PM approval | 15% | 100% |  |  | revised template file for upload Original Budget & MH Planning, additional feature master Project ExRate. status : done
|  |  |  | 4. Project Execution Phase | 50% | 100%
|  |  |  | a. Project Contract change order |  |  |  |  | additional feature, status : done
|  |  |  | b. Man Hour changes |  |  |  |  | done
|  |  |  | c. Approved Budget changes |  |  |  |  | done
|  |  |  | d. Internal Transfer |  |  |  |  | done
|  |  |  | e. Master data Vendor / Subcon |  |  |  |  | revised, Get data from SOFI (no input / update @ PCCIS) - done
|  |  |  | f. Commitment (WO / PO / Contract) |  |  |  |  | additional feature, Upload PCOM data as PO reference (status : done) PO/WO amendment history (status : done)
g. Monthly Actual Costs / Expenses
|  |  |  | 1. Register Invoice (with & without PO/WO) |  |  |  |  | additional feature, Inv / RFP without WO/PO - done ; revise invoice detail form
|  |  |  | 2. RFP Authorization |  |  |  |  | additional feature, status : done
|  |  |  | 3. Interface to & from SOFI |  |  |  |  | done
|  |  |  | 4. Collect other Project Cost (inputted directly to SOFI by FAD) |  |  |  |  | on going
|  |  |  | h. Monthly Cash In / Invoice to Client (Monitoring Payment Receipt status) |  |  |  |  | revised, additional function to monitor invoice to client & payment receipt status, export to Excel. Status : done
|  |  |  | i. Field Expense / Advance Payment - FAD |  |  |  |  | on going
|  |  |  | j. Local Content |  |  |  |  | done
|  |  |  | 5. Project Cost Control / Reporting | 25% | 100% |  |  | on going
|  |  |  | a. Monthly Actual Cost Work Performed (ACWP) Report |  |  |  |  | additional feature : Cost Report by original currency (status : done)
|  |  |  | b. PO Balance Status Report |  |  |  |  | done
PCCIS Summary |  |  |  |  | 100% | 100% |  |  | this week issue : - Block A Pj : register commitment (WO), upload monthly MHSpent (multi mh rate) - DS maintenance & DS ACO-045 : cont to input commitment (PO/WO), input invoice @ PCCIS then matching invoice with RFP @ SOFI with payment checking status, get monthly mhspent Feb2016 directly from MICA - Juanda Airport Pj : cont to collect project cost from SOFI, get monthly mhspent Feb2016 directly from MICA - Revise RFP numbering format (generated by PCCIS), revise store procedure to submit invoice to SOFI
Request for Advance Payment | Indra & Jeremy | FAD | Start | 1. Gathering requirements & Study existing system / procedure | 5% | 100% |  |  | done
|  |  |  | 2. Create Flow chart, Identify modification on SOFI, Create database structure | 10% | 100% |  |  | done
3. Development Phase, breakdown per module
|  |  |  | a. Request for Advance & Approval module | 15% | 95% |  |  | revised, Kuriyama san requested no need e-approval, the approval will be manually distributed up to management & signed on the paper / hard copy
|  |  |  | b. Interface for Advance between MICA - SOFI | 15% | 95% |  |  | on going
|  |  |  | c. Settlement & Approval module | 30% | 95% |  |  | revised, Kuriyama san requested no need e-approval, the approval will be manually distributed up to management & signed on the paper / hard copy
|  |  |  | d. Interface for settlement between MICA - SOFI | 15% | 95% |  |  | on going
|  |  |  | e. Interface / connection to Project Cost Control (FER) | 10% | 95% |  |  | on going
|  |  |  | f. Project Petty Cash Flow monitoring | 0% | 80% |  |  | no need this module, because for Request for Advance Project (Petty Cash) wont be entry to system. Kuriyama san requested to proceed manually.
Advance Payment Summary |  |  |  |  | 100% | 95.75% |  |  | this week issue, cont prepare RFAP JO/Consortium version
PCCIS Progress |  |  |  |  | 97.88%
C. GA System (JOB CODE 7-4004-00-0002)
GA Requisition & Quotation System | Ade Perdana/Das | GAD | On Going | Gathering requirements & Assesment current System | 5% | 100%
|  |  |  | Develop Plan & Design Database | 10% | 100%
|  |  |  | 1. Requisition Modul | 25% | 100% |  |  | Generate requisition to Quotation or Advance workflow, change as per requested by Ms. Neti - GAD
a. Entry Requisition Slip
b. Requisition Summary
c. Approval workflow
d. Requisition approval
|  |  |  | 2. Quotation Modul | 25% | 92% |  |  | Add Quotation attachment (vendor document). Quotation item can be edited. Quotation workflow change
a. Manage Vendor data
b. Collect quotation based on requisition
c. Quotation approval
|  |  |  | 3. Create interface to PO System @ SOFI | 15% | 90%
|  |  |  | 4. Monitoring & Reporting | 20% | 100%
GA Requisition & Quotation System Summary |  |  |  |  | 100% | 96.5% |  |  | this week issue : - additional delivered date per item - additional attachment vendor (DO) per item - additional activity after waiting received item - additional & modification report
Vehicle Reservation (Request for Vehicle) | Das/Ade Perdana | GAD | On Going | 1. Reservation form entry | 50% | 100%
|  |  |  | a. Multiple users and vehicles in one reservation |  |  |  |  | done
|  |  |  | b. Multiple vehicle schedules per reservation and multiple transaction per vehicle in one day |  |  |  |  | done
|  |  |  | c. Send notification email to Approver (PM / Dept. Manager / Div. Manager) |  |  |  |  | done
|  |  |  | d. Vehicle Management form |  |  |  |  | done
|  |  |  | 2. Approver module | 20% | 100% |  |  | create job agent to pass approval to representative
|  |  |  | a. On Behalf / Representative module |  |  |  |  | done
|  |  |  | b. Approval workflow and determination logic |  |  |  |  | done
|  |  |  | 3. Monitoring / Tracking for employee and GAD | 15% | 100% |  |  | done
a. Employee able to see and monitoring their request status
b. GAD able to montoring and tracking vehicle distribution distribution and avalaibility per day (requested by Ms. Ari)
|  |  |  | 4. Reporting module | 10% | 100% |  |  | done
a. Monthly vehicle report for GAD
b. Vehicle user report as per requested by user
c. Detail of Driver monthly report
|  |  |  | 5. Server agents job for automatic reject (expired reservation) and sending remainder message for GAD and approvers on unprocessed request | 5% | 100% |  |  | done
Vehicle Request Summary |  |  |  |  | 100% | 100% |  |  | edit approval & initiation
Circle News Site | Das | GAD | on study | Gathering requirements & Assesment current System | 10%
|  |  |  | Develop Plan and Site Design | 10%
|  |  |  | Form Create, Edit, Delete and Upload Magazines Files | 40%
|  |  |  | Digital Magazine (swf file) player modul | 25%
|  |  |  | Form Create, Edit, Delete Admin List | 15% | 100%
P.O System | Das | GAD | HOLD | Gathering requirements | 5% | 100% |  |  | Development continue on SOFI, ITD Dev will develop system from Requisition up to Quotation only, after that send to SOFI as PO
|  |  |  | Development design & Database | 10% | 100%
|  |  |  | User Interface | 10% | 80%
|  |  |  | Form Input PO, Currency, Category, Items | 40% | 100%
|  |  |  | PO montoring Form | 20% | 100%
|  |  |  | Reporting / Convert PO Form to Excel (Carbon Paper) | 15% | 0%
PO System Summary |  |  |  |  | 100% | 84%
GA System Progress |  |  |  |  | 93.5%
D. IT SYSDEV (JOB CODE 7-4004-00-0000)
ITD Resignation Check List | Deden/Indra |  |  | 1. Entry form by TS | 15% | 100%
a. Employee Information
b. Defining Action for every check list
|  | ITD | On Going | 2. Update chek list status form | 40% | 100%
|  |  |  | 3. Display employee resign and it's ITD chek list status with filter | 30% | 100%
|  |  |  | 3. Syncronisation employee resign status from MICA to ITD Resignation system | 10% | 100%
|  |  |  | 4. Update emp. status in Inventory application once chek list action 'Done' | 5% | 100%
ITD Resignation Check List Summary |  |  |  |  | 100% | 100%
BBQOC | Jeremia | QHSSE | On Going | 1. Gathering Requirement & Study Exixsting System / Procedure | 10% | 100% |  |  | on going
|  |  |  | 2. Create Flow Chart,Create Database Structure | 10% | 100% |  |  | on going
|  |  |  | 3. Form Data Entry | 30% | 85% |  |  | on going
|  |  |  | 4. Form Monitoring | 10% | 85% |  |  | on going
|  |  |  | 5. Form Report | 30% | 85% |  |  | on going
|  |  |  | 6. Mail Notifikasi | 10% | 0%
PJLC Summary |  |  |  |  | 100% | 79.5% |  |  | under reviewed by Pak Syahgol, additional feature from Pak Hilman
(Share Point Dev)PJLC | Ade Perdana/Jemi/Das | DED/CBD/PMD | HOLD | 1. Project Document Center | 15% | 100% |  |  | done
|  |  |  | 2. Knowledge Database /Lesson & Learn New | 20% | 100% |  |  | Under Review pak Arief Revisi : - tipe FWBS di ganti jadi Metadata - tambah link ke portal - IMPACT ON BUDGET & SCHEDULE dipisah - Link di menu awal ke List bukan ke new item - Tambahan kolom discipline dan Review / Comment - tambah default value di kolom, calculation, objective, background, recomendation, reference - rubah kolom Year dan Project Type
|  |  |  | 3. Project Lifecycle Form (1 - 5) PMD | 35% | 90% |  |  | Under Review
|  |  |  | 4. Online MOM | 10% | 90% |  |  | Under Review
|  |  |  | 5. DE Timesheet (FWBSv6) | 20% | 90% |  |  | Under Review ( Can Change depent on PJ Report Requirment) | to be updated to latest
PJLC Summary |  |  |  |  | 100% | 92%
SYSDEV Progress |  |  |  |  | 90.5%
OVERALL PROGRESS |  |  |  |  | 91.72%
Portal Maintainer | Ade P/Jemi
Overall (7-40XX) (plan)
IT Inventory | Ade P/Jemi/Das |  |  | Overall (7-40XX) (actual/forecast) | 91.72%
HR System (plan)
UI Make over | All |  |  | HR System (actual) | 85%
PCCIS (plan)
|  |  |  | PCCIS (actual) | 97.88%
GA System (plan )
|  |  |  | GA System (actual) | 93.5%
Sys Dev (plan )
|  |  |  | Sys Dev (actual) | 90.5%